## ISER Timeline
AVC ACCJC Institutional Self-Evaluation Report (ISER) Timeline 2021-2024
Tasks | Start | Finish | Duration | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01
AVC's Accreditation Liaison Officer (ALO) coordinates initial ISER trainings with the President's Office and ACCJC's Staff Liaison for AVC | 2021-01-01 | 2021-01-31 | 1 month
Board Training-Accredition and Governing Board Roles & Responsibilities with AVC's Staff Liaison Gohar Momjian | 2021-02-08 | 2021-02-08 | 1 hour
ISER Kick-Off Training with AVC's Staff Liaison Gohar Momjian for Admin. Council & Department Chairs | 2021-02-11 | 2021-02-11 | 3 hours
Academic Senate's Appointment of the Faculty Accreditation Chair (FAC) | 2021-03-01 | 2021-03-31 | 1 month
Accreditation Committee Chairs (FAC & ALO) hold initial ISER meeting with Standard Leaders | 2021-04-01 | 2021-04-15 | 2 weeks
Accreditation Committee Chairs (FAC & ALO) hold ISER meeting with Standard Leaders & their Standard Teams | 2021-04-15 | 2021-05-15 | 4 weeks
ISER Development-Standard Teams meet and work on respective Standards in concert with the FAC & ALO | 2021-05-01 | 2021-08-30 | 4 months
Accreditation Committee meets monthly to share progress with the ISER and Standards | 2021-09-01 | 2022-04-30 | 8 months
ACCJC Advanced ISER Training & support from AVC's Staff Liaison Gohar Momjian | 2022-03-24 | 2022-03-24 | 1 hour
First Draft of ISER to Academic Senate, Executive Council, the President & Board, and other constituents | 2022-04-01 | 2022-06-30 | 3 months
Standard Teams meet and work on respective Standards in concert with the FAC & ALO | 2022-07-01 | 2022-08-30 | 2 months
Accreditation Committee meets monthly to share progress with the ISER and Standards | 2022-08-01 | 2022-10-30 | 3 months
Second Draft of ISER to Academic Senate, Executive Council, the President & Board, and other constituents | 2022-10-01 | 2022-11-30 | 2 months
Accreditation Committee meets monthly to share progress with the ISER and Standards | 2022-11-01 | 2022-12-31 | 2 months
Final Draft of ISER to Academic Senate, Executive Council, the President & Board, other constituentsand, and to ACCJC | 2022-11-15 | 2022-12-15 | 1 month
Team ISER Review & Core Inquiries (formative component of peer review) | 2023-01-01 | 2023-04-30 | 4 months
Preparation for Focused Site Visit | 2023-05-01 | Fall 2023 | ~5 months
Focused Site Visit (summative component of peer review) | 2023-09-18 | 2023-09-22 | <1 week
Draft Team Report | Fall 2023 | Fall 2023 | TBD
Final Team Report | Fall 2023 | Fall 2023 | TBD
Commission Decision Regarding AVC's Reaffirmation of its Accreditation | 2024-01-01 | 2024-01-31 | TBD

## ISER Tasks Overview (hidden)
ISER Contents
A. | Introduction | College Lead | Helpers
College History
Student Enrollment Data |  | Meeta & Svetlana | Vanessa E.
Labor Market Data |  | Meeta & Svetlana | Vanessa E.
Demographic Data |  | Meeta & Svetlana | Vanessa E.
Socio-economic Data |  | Meeta & Svetlana | Vanessa E.
Sites
Specialized or Programmatic Accreditation
B. | Presentation of Student Achievement Data and Institution-set Standards
C. | Organization of the Self-Evaluation Process
D. | Organizational Information
E. | Certification of Continued Compliance with Eligibility Requirements
F. | Certification of Continued Institutional Compliance with Commission Policies
G. | Institutional Analysis
Standard I: Mission, Academic Quality and Institutional Effectiveness, and Integrity |  | Ed Knudson, Meeta Goel
A. | Mission
B. | Assuring Academic Quality and Institutional Effectiveness | Meeta & Svetlana | Vanessa E.
C. | Institutional Integrity
Standard II: Student Learning Programs and Support Services |  | Isabelle Saber, Erin Vines
A. | Instructional Programs
B. | Library and Learning Support Services | Library (Plus Meeta & Van) and Learning Center Staff | Morenike
C. | Student Support Services
Standard III: Resources |  | Ed Knudson, VPAS
A. | Human Resources | Harmony Miller, Rhonda Burgess, Terry Cleveland
B. | Physical Resources | Dawn Mcintosh, Erin Tague, Ron Benedetti
C. | Technology Resources | Rick Shaw, Mike Dioquino
D. | Financial Resources | Sarah Miller
Standard IV: Leadership and Governance |  | Ed Knudson with BOT, Van Rider, ASO President
A. | Decision-Making Roles and Processes
B. | Chief Executive Officer
C. | Governing Board
D. | Multi-College Districts or Systems | N/A
H. | Quality Focus Essay