## Sheet1
2010 CAPITAL OUTLAY PROJECT REVIEW
SPBC Facilities Sub Group Project Review - FINAL RECOMMENDATIONS
PROJECT | PRIORITY | RANKING | PROJECT NAME | INITIAL COST EST. | REVISED COST EST. | COMMENT | PROJECT START
A-A |  | 1 | Replace Language Arts Roof | 143621 | NONE | Required for State Compliance | SPRING 2011
A-B |  | 2 | Replace Gymnasium Roof | 78450 | NONE | Required for State Compliance | SPRING 2011
A-C |  | 3 | Repair Roofs - LH | 45035 | NONE | Required for State Compliance | SPRING 2011
A-D |  | 4 | Replace HVAC at B/TE6 | 14000 | NONE | Required for State Compliance | SPRING 2011
B-A |  | 5 | Campus Waste & Recycling Center | 180000 | 220000 | CHANGE - Add compactor cost | SPRING 2011
C-A |  | 6 | Elevator Renovation | 400000 | NONE |  | SPRING 2011
C-D |  | 7 | Campus Roadway Safety & Naming | 400000 | 250000 | CHANGE - Reduce SOW and Cost | SPRING 2011
Traffic Study-Signage/10 Intersections/Rd. Signs (Priority)
C-H |  | 8 | Welding Lab Upgrades | 320000 | 25000 | CHANGE - Reduce SOW & Cost/Safety Upgrades Only | SPRING 2011
C-G |  | 9 | Upgrade Existing Modular Buildings to DSA Std. | 35000 | NONE | Only for Modular Buildings Kept Long-Term | SPRING 2011
C-B |  | 10 | Demolish South Central Plant/Renovate Area | 488000 | 403000 | CHANGE - Reduce Area Improvement Cost | SPRING 2011
$268,000 SCP/$135,000 SSV Vestibule
C-I |  | 11 | South Exterior Student Center Renovation | 325000 | 235000 | CHANGE - Reduce SOW & Cost | SPRING 2011
C-E |  | 12 | H&S Building - Café/Kitchen Buildout | 390000 | NONE |  | SPRING 2011
C-F-A |  | 13 | LS1/LS2/OF3 Building Renovation | 983000 | NONE |  | SPRING 2011
C-N |  | 14 | Student & Employee Campus Amenities | 98000 | NONE |  | SPRING 2011
C-P |  | 15 | Chilled Water Loop Connections | 360000 | NONE | Connect CDC, SCT, FA Buildings | SPRING 2011
N-1 |  | 16 | FA3 Sound Attenuation Renovation | N/A | 99300 | NEW REQUIREMENT | SPRING 2011
C-Q-A |  | 17 | Purchase Leased Modular Buildings - Phase I | 550000 | 324757 | Phase 1 - Purchase T503, T504, T850, T851 See Attached Payback Schedule | SPRING 2011
E-G |  | 18 | Stadium Turf Protector Covers | 123000 | 150000 | CHANGE - Cost Revised | SPRING 2011
C-C |  | 19 | Demolish Old Science Buildings/Renovate Area | 670000 | 455000 | CHANGE - Reduce SOW and Cost Buildings Do Not Meet Structural Standards Project Underfunded by $90,000 DW/1-28-11 | FALL 2012
C-M |  | 20* | APL Renovation of Vacated Space | 2395000 | 250000 | CHANGE - Reduce SOW & Cost | 2012/2013
C-L |  | 21* | Building T800 Renovation | 237000 | NONE |  | 2012/2013
N-4 |  | 22* | Renovation of Anthropology Classrooms - LS1 | N/A | 132000 | NEW REQUIREMENT | 2012/2013
N-5 |  | 23** | T502 Renovation for Community Education | N/A | 35000 | NEW REQUIREMENT (Space utilization and financial analysis to be completed prior to action) | 2012/2013
E-D |  | 25 | Choral Room Chair Replacement | 150000 | NONE |  | 2012/2013
C-K |  | 26 | Campus Message Sign | 350000 | 256000 | CHANGE - Reduce SOW & Cost/Donation Opportunity | 2012/2013
N-2 |  | 27** | SSV Building - Student Services Expansion | N/A | 2243000 | NEW REQUIREMENT - Project to be phased due to funding constraints. (Space utilization and financial analysis to be completed prior to action) | 2012/2013
B-B |  | 28 | Marauder Stadium Restroom | 792000 | 426000 | CHANGE - Modular Restroom Behind Fieldhouse | 2012/2013
C-Q-B |  | 29** | Purchase Leased Modular Buildings - Phase II | 450000 | 499908 | Phase 2 - Purchase T100, T300, T502 (Space utilization and financial analysis to be completed prior to action) | 2012/2013
B-C |  | 30 | Grounds Support Building | 435000 | 85000 | CHANGE - Shelter only | 2012/2013
C-V |  | 31 | Library Renovation | 1750000 | NONE | Project to be phased due to funding constraints | 2012/2013
E-O |  | 32 | Tennis Court Refurbishment | 130000 | 220000 | CHANGE - Estimate Revised | 2012/2013
E-B |  | 33 | Gymnasium Floor Replacement | 400000 | NONE |  | 2012/2013
E-C |  | 34 | Gymnasium Ceiling Renovation | 250000 | NONE |  | 2012/2013
C-F-B |  | 35 | NEW - LS1/LS2/OF3 HVAC Renovation | N/A | 1220000 | NEW REQUIREMENT - Project cannot be phased | 2012/2013
N-3 |  | 36 | Softball Field Netting at Wall | N/A | 18000 | NEW REQUIREMENT | 2012/2013
NOT RECOMMENDED - DONATION OPPORTUNITY
C-N |  |  | Additional Campus Outdoor Seating | TBD |  | ASO & DONATION Contributions
C-S |  |  | Information Kiosks | TBD |  | ASO & DONATION Contributions
C-J |  |  | Performing Arts Theatre Water Feature | 176000 |  | ASO & DONATION Contributions
C-R |  |  | Health & Science Building Virtual Science Lab | 1000000 |  | GRANT & DONATION Contributions
C-X/Y |  |  | Baseball Stadium Seating/Lighting | 830000 |  | DONATION Contributions
C-Z |  |  | Softball Stadium Lighting | 510000 |  | DONATION Contributions
NOT RECOMMENDED
C-T |  |  | Palmdale Campus Planning | 750000 |  | Projected local and state funding delays will place planning period beyond Mesure R funding period.
C-U |  |  | Auto Body Wall Stain | 21000
B-D |  |  | Marauder Stadium 8' Security Fence | 16500
|  |  | Start Project - Spring 2011 | 4254163
|  |  | Start Project - Fall 2012 | 455000
|  |  | Fall 2012 - Priority 1 | 654000
|  |  | 2012/2013 - Priority 2 | 2649000 | PENDING FUNDING AVAILABILITY
|  |  | 2012/2013 - Priority 3 | 4868908 | PENDING FUNDING AVAILABILITY
* Dependent on final rate of return on bond funds
** Dependent on results of space utilization study and financial analysis.